## Slide 1
TACO BELL | ARN
The Pipeline Bible
Field Development Playbook & Training Manual
How a disciplined, sequenced pipeline protects the schedule — and how to run it.
Built fresh · Made to order · Served on time.
“We focus on making the tacos, not the sausage.”
Multi-State Field Development (CA · WI · CO · NM · TX · IL) · Companion to the ARN Pipeline Bible workbook · As of 6/25/26

## Slide 2
PIPELINE PLAYBOOK
Why the Bible Matters
TACO BELL | ARN
2
The spreadsheet isn't a tracker — it's a playbook. Each field is a gate, and the column order is the critical path that protects your opening date.
Sequence
Every site moves stage-by-stage. The order things happen in is what optimizes the schedule.
No missed steps
Each required field is a checkpoint. A blank in an early column is a gate not yet cleared.
Accountability
Owners + due dates + stoplight flags make slippage visible the moment it happens.
Measurement
Status, timing, and risk roll up to one dashboard — manage by exception, weekly.
Executed well and managed closely, this is the single most effective field-development management tool ARN has.
The Taco Bell way: a great deal, like a great taco, is built in order — skip a layer and it falls apart.

## Slide 3
PIPELINE PLAYBOOK
How the Workbook Works
TACO BELL | ARN
3
DASHBOARD
KPIs for status, timing & accountability — the weekly management view.
Stage tabs
One tab per pipeline stage (SIP → … → Opened). A site lives on the tab matching its stage.
Columns = gates
Read left-to-right: each column is the next thing that must happen, in order.
Stoplight (RAG)
STATUS, RISK, Action Flag & SOP auto-color green / amber / red so problems pop.
Renewal Tracker
Separate asset-management track for lease renewals & option-notice critical dates.
Rule of thumb: the template is the bible — every other sheet conforms to it. Added columns are tagged so the canonical structure stays clean.

## Slide 4
PIPELINE PLAYBOOK
The Front Door — Your Landing Page
TACO BELL | ARN
4
OPENS FIRST
The workbook lands here every time — one calm screen instead of 30-plus tabs.
6 live KPI cards
Portfolio counts, renewals due, data gaps and this-week actions update themselves on open.
One-tap navigation
Branded buttons jump straight to the Dashboard, Add / Close, Renewals, Cell Sites and Excess Properties.
Built for everyone
Exec, field RE and finance each have a labeled path in — no spreadsheet skills required.
Always current
Every number recomputes on open — the front page is never stale.
Rule of thumb: if you are not sure where to go, go to the Front Door — it routes you to the right tab.

## Slide 5
PIPELINE PLAYBOOK
The Pipeline at a Glance
TACO BELL | ARN
5
Eight development stages — plus a parallel renewals track for the existing portfolio.
1 SIP
Tour, score, qualify
● < $5K
›
2 LOI
Negotiate terms
● $5–15K
›
3 Legal / Lease
Execute lease/PSA
● $40–80K
›
4 Due Diligence
Entitlements, site plan
● $75–150K
5 Committee
Capital approval
● ~$1.5–2.5M*
›
6 Permitting
CDs → permit
● $75–150K
›
7 Construction
Possession → build
● $1.2–2.2M
›
8 Open · Live Más
Open & hand off
● Revenue in
● = risk level (green / amber / red) · $ = planning estimate of capital at risk — verify to ARN actuals.
PARALLEL TRACK — RENEWALS: existing restaurants are managed on the Renewal Tracker. The option-notice deadline is the critical date; SOP margin drives the renew / renegotiate / relocate / close decision.

## Slide 6
PIPELINE PLAYBOOK
The Development Lifecycle — Baseline from Real Deal Data
TACO BELL | ARN
6
Median elapsed days per phase, computed from the prior rollout's actual milestone dates. Permitting reset to current ARN markets.
Transparency — the machine behind these numbers: 22 completed openings + 101 committee-approved projects. Per-phase sample (n) shown in the legend.
Chart: 
| LOI→DD 68d (n=11) | DD→Approval 91d (n=33) | Approval→Permit ~1 yr* | Permit→Const 29d (n=20) | Construction 130d (n=22)
Median days | 68 | 91 | 365 | 29 | 130
BASELINE — LOI → OPEN
≈ 683 days (~22 months)
PRE-APPROVAL — ~159 days
LOI → committee. Lower commitment; you can still walk.
POST-APPROVAL — ~524 days
Capital committed: permitting & construction. The clock runs hard.
THE LONG POLE Approval → Permit ≈ ~1 year (ground-up) in current ARN markets — conversions potentially ~6 months. Far above construction (~130d). Front-load entitlements.
*Permitting = current ARN markets ~1 yr ground-up / ~6 mo conversion; historical baseline was ~205d. Other phases = prior-rollout medians (n in legend). Track ARN variance in the bible.

## Slide 7
PIPELINE PLAYBOOK
Stage 1 — SIP (Sites in Process)
TACO BELL | ARN
7
SIP
▼ YOU ARE HERE
›
LOI
›
Legal/ Lease
›
Due Dil. & Entitle
›
Committee Approval
›
Permitting
›
Construction
›
Open
Purpose
Source, tour, score and qualify candidate sites against the trade-area strategy.
Gate to advance
Site qualified and engaged (offer / LOI intent) → STATUS = In Negotiation
OWNER
Real Estate
TYPICAL DURATION
Ongoing
CAPITAL & RISK
$$$$
LOW
EST. $ AT RISK
< $5K
Sourcing & tour time — little cash committed.
KEY BIBLE FIELDS
Date Toured
Trade Area
Size
For Sale / Lease
Price
Aerial / Site Plan / Flyer
STATUS
DON'T-MISS STEPS
▪ Run the site scorecard & trade-area fit
▪ Confirm drive-thru feasibility & stacking
▪ Secure all asset docs (aerial, plat, flyer)
Pitfall Chasing sites that don't fit the trade-area strategy — discipline here saves money downstream.

## Slide 8
PIPELINE PLAYBOOK
Stage 2 — LOI (Letter of Intent)
TACO BELL | ARN
8
SIP
›
LOI
▼ YOU ARE HERE
›
Legal/ Lease
›
Due Dil. & Entitle
›
Committee Approval
›
Permitting
›
Construction
›
Open
Purpose
Negotiate and execute non-binding deal terms before spending on diligence.
Gate to advance
Executed LOI / LL work exhibit
OWNER
Real Estate
TYPICAL DURATION
~68 d → DD (baseline)
CAPITAL & RISK
$$$$
LOW
EST. $ AT RISK
$5–15K
Non-binding terms — minimal cash; sets the deal.
KEY BIBLE FIELDS
Offer
Price / Rate
LOI Sent
LOI Executed
DON'T-MISS STEPS
▪ Lock rent, TI, term & options, exclusivity
▪ Build in a diligence period & outs
▪ Define delivery condition
Pitfall A vague LOI gets renegotiated later. No DD-out = capital at risk before you can walk.

## Slide 9
PIPELINE PLAYBOOK
Stage 3 — Legal / Lease (or PSA)
TACO BELL | ARN
9
SIP
›
LOI
›
Legal/ Lease
▼ YOU ARE HERE
›
Due Dil. & Entitle
›
Committee Approval
›
Permitting
›
Construction
›
Open
Purpose
Draft, negotiate and fully execute the lease or purchase agreement.
Gate to advance
Lease / PSA fully executed (LS = Lease Status)
OWNER
Legal + Real Estate
TYPICAL DURATION
4–10 weeks
CAPITAL & RISK
$$$$
HIGH
EST. $ AT RISK
$40–80K
Lease / PSA execution = first major commitment; + title / Phase I / survey.
KEY BIBLE FIELDS
LS (Lease Status)
Lease / Committee Comments
Title / PTR
Phase I
ALTA Survey
DON'T-MISS STEPS
▪ Pull title/PTR & estoppels
▪ Order Phase I environmental
▪ Order ALTA survey
Pitfall Starting capital-heavy diligence before terms are locked burns money on dead deals.

## Slide 10
PIPELINE PLAYBOOK
Stage 4 — Due Diligence & Entitlements
TACO BELL | ARN
10
SIP
›
LOI
›
Legal/ Lease
›
Due Dil. & Entitle
▼ YOU ARE HERE
›
Committee Approval
›
Permitting
›
Construction
›
Open
Purpose
Prove the site is buildable — zoning, site plan, re-plat, utilities, signage.
Gate to advance
Entitlements / site plan approved; DD cleared
OWNER
Real Estate
TYPICAL DURATION
~91 d intake→approval (baseline)
CAPITAL & RISK
$$$$
MED–HIGH
EST. $ AT RISK
$75–150K
At-risk capital — survey, civil & entitlement consultants.
KEY BIBLE FIELDS
Re-Plat Start / Complete
Site / Floor Plan
Signage Research
Utilities
DON'T-MISS STEPS
▪ Secure zoning / CUP & re-plat
▪ Confirm civil, utilities & access
▪ Lock signage & drive-thru approvals
Pitfall Entitlement delay is the #1 schedule killer — start early and run it in parallel with legal.

## Slide 11
PIPELINE PLAYBOOK
Stage 5 — Committee Approval (RE Committee)
TACO BELL | ARN
11
SIP
›
LOI
›
Legal/ Lease
›
Due Dil. & Entitle
›
Committee Approval
▼ YOU ARE HERE
›
Permitting
›
Construction
›
Open
Purpose
Secure capital approval at the Real Estate Committee.
Gate to advance
RE Committee Date — approved
OWNER
Exec + Real Estate
TYPICAL DURATION
1–2 weeks (cycle-bound)
CAPITAL & RISK
$$$$
APPROVE
EST. $ AT RISK
~$1.5–2.5M*
Capital is formally authorized here — go / no-go gate.
KEY BIBLE FIELDS
RE Committee Date
RISK
A&C Package
Proforma
DON'T-MISS STEPS
▪ Complete A&C package & proforma
▪ Assign a risk rating
▪ Attach site scorecard & comps
Pitfall An incomplete package = deferral = a missed committee cycle and weeks of lost time.

## Slide 12
PIPELINE PLAYBOOK
Stage 6 — Permitting
TACO BELL | ARN
12
SIP
›
LOI
›
Legal/ Lease
›
Due Dil. & Entitle
›
Committee Approval
›
Permitting
▼ YOU ARE HERE
›
Construction
›
Open
Purpose
Complete construction documents and obtain the building permit.
Gate to advance
Permit Ready / permit issued
OWNER
Construction
TYPICAL DURATION
~1 yr ground-up · ~6 mo conversion
CAPITAL & RISK
$$$$
MED
EST. $ AT RISK
$75–150K
CD / architect fees + permit costs.
KEY BIBLE FIELDS
Permit Ready
Last Permit Date
CDs Complete
DON'T-MISS STEPS
▪ Finish CDs & submit early
▪ Track jurisdiction review cycles
▪ Clear off-site / utility permits
Pitfall Underestimating municipal review time. Build the real review cycle into the schedule.

## Slide 13
PIPELINE PLAYBOOK
Stage 7 — Construction
TACO BELL | ARN
13
SIP
›
LOI
›
Legal/ Lease
›
Due Dil. & Entitle
›
Committee Approval
›
Permitting
›
Construction
▼ YOU ARE HERE
›
Open
Purpose
Take possession and build the restaurant.
Gate to advance
Possession → Start Construction → Construction complete / CO
OWNER
Construction
TYPICAL DURATION
~130 d (baseline)
CAPITAL & RISK
$$$$
PEAK
EST. $ AT RISK
$1.2–2.2M
Peak cash outlay — construction budget + FF&E.
KEY BIBLE FIELDS
Poss Date
Start Const
Const Duration
Sched Opening
DON'T-MISS STEPS
▪ Order long-lead equipment (FF&E) at permit
▪ Run hiring & training in parallel
▪ Schedule CO / final inspection
Pitfall Not ordering long-lead items early, and hiring serially instead of in parallel with the build.

## Slide 14
PIPELINE PLAYBOOK
Stage 8 — Open · Live Más
TACO BELL | ARN
14
SIP
›
LOI
›
Legal/ Lease
›
Due Dil. & Entitle
›
Committee Approval
›
Permitting
›
Construction
›
Open
▼ YOU ARE HERE
Purpose
Open the restaurant and hand off to Operations — opening day is the Live Más payoff.
Gate to advance
Opening date achieved
OWNER
Ops
TYPICAL DURATION
Open day → 90 days
CAPITAL & RISK
$$$$
REVENUE
EST. $ AT RISK
Revenue in
Spend complete — sales begin. Live Más.
KEY BIBLE FIELDS
Sched Opening
Period Opening
Grand-Opening Promo
DON'T-MISS STEPS
▪ Execute grand-opening marketing
▪ Run a 90-day post-open review
▪ Load lease abstract into the Renewal Tracker
Pitfall No post-open review, and renewal/option dates never get loaded — re-creating the original miss.

## Slide 15
PIPELINE PLAYBOOK
Completing the Lifecycle — Add, Close & Learnings
TACO BELL | ARN
15
OPEN
›
OPERATE
›
RENEW
›
CLOSE
↻
LEARN
▼ YOU ARE HERE
A restaurant's life doesn't end at Open — the Bible tracks it cradle-to-grave, and the grave feeds the next site:
▪ Add a Restaurant — a site graduates off SIP into the Master through a validated intake form (Restaurant # · address · city · state required).
▪ Operate & Renew — performance, renewals and remodels keep it a green contributor (covered earlier).
▪ Close a Restaurant — a guided form captures Close Date · Reason · Sales / SOP at close · lease disposition · required Learnings.
▪ Archive — the full record moves to RESTAURANT CLOSURES with Years Open; QA blocks any restaurant from living in both Open and Closures.
▪ Learnings loop — closure reasons recalibrate SIP scoring, so the next hunt avoids the same mistake.
The payoff: every opening and every closing makes the next siting decision smarter — nothing is lost.

## Slide 16
PIPELINE PLAYBOOK
Renewals — Protecting the Existing Portfolio
TACO BELL | ARN
16
Renewals run in parallel to the development pipeline. The option-notice deadline is a hard, unforgiving date — miss it and you can forfeit the option or fall into holdover.
THE CRITICAL DATE
▪ Track LL Notice Date for every lease
▪ Notice Status auto-flags On Track / Due <180d / <90d / Overdue
▪ Work backward from the deadline — start early
▪ Load every new restaurant's dates the day it opens
THE DECISION — SOP TRIAGE
▪ Green ≥25% renew on strong terms
▪ Amber 15–25% renegotiate / improve economics
▪ Red <15% fix rent or relocate / close
5 renewals in flight today:
▪ #1968 Albuquerque — SOP 26.6% (green), In Review; proposed 10-yr + 4×5 under review
▪ #28512 Bellflower — SOP 2.8% (red), At Risk; must cut rent or close, remodel tied to deal
▪ #2828 Long Beach — SOP 24.1% (amber); hard expiry 12/31/30, align 3-brand renewals
▪ #28521 Lomita — SOP 17.2% (amber), contact made; #3186 Centennial — 24.0% (amber), not yet started

## Slide 17
PIPELINE PLAYBOOK
Critical Path & Schedule Optimization
TACO BELL | ARN
17
The column order is the critical path. Two habits protect the opening date:
RUN TRACKS IN PARALLEL
▪ Legal/lease + entitlements at the same time
▪ Order long-lead FF&E the moment permit is in sight
▪ Hire & train while construction runs
▪ Renewals worked years ahead of expiry
TREAT EVERY FIELD AS A GATE
▪ A blank required cell = a step not done
▪ Dates create the schedule; variance shows slippage
▪ Days-to columns count down automatically
▪ Manage by exception: red & overdue first
Schedule math, automated in the bible:
▪ Days Since Toured / Days to Open / Sched Var update daily via TODAY()
▪ Action Flag turns red the day a Next Step Due passes
▪ Notice Status flags renewals before the window closes

## Slide 18
PIPELINE PLAYBOOK
Roles, Accountability & Weekly Cadence
TACO BELL | ARN
18
WHO OWNS WHAT
Real Estate
Sourcing, LOI, entitlements, renewals
Construction
Permitting, build, FF&E, CO
Legal
Lease/PSA, title, estoppels
Ops
Opening, staffing, post-open
Exec
Committee approval, capital, strategy
THE WEEKLY PIPELINE REVIEW
▪ Open the DASHBOARD — read Overdue Actions, status mix, days-to-open, renewal flags
▪ Sort SIP by Action Flag: clear every Overdue and Due-Soon item first
▪ Review every Blocked / At-Risk site — decide: push, pause, or kill
▪ Check renewals: any Notice Status amber/red gets a dated next step
▪ Update Lead + Next Step + Due on every active row before you close the meeting

## Slide 19
TACO BELL | ARN
The Workbook — A Tab-by-Tab Roadmap
What each tab tracks, where it sits in development, and why it's critical.

## Slide 20
PIPELINE PLAYBOOK
Workbook Scorecard — All Tabs at a Glance
TACO BELL | ARN
20
Tabs run in development order; the Master (Open Restaurants) is the destination. Each tab is a gate — the column order is the critical path.
Tab
Role in the lifecycle
Owner
# Fields
Why it's critical
DASHBOARD
Command center / KPI rollup
Exec / All
KPIs
Run the weekly review on one screen
SIP
Stage 1 — site inception
Real Estate
41
Every deal is born here
Pre-DD Pipeline
Sourcing → LOI (pre-diligence)
Real Estate
33
Locks the deal before the capital ask
Due Diligence
DD intake → diligence / entitlements
RE / Legal
34
Proves buildability; #1 schedule risk
Committee Approved
Capital approved at RE Committee
Exec / Finance
37
The go / no-go capital gate
2026 Openings YTD
Construction → open
Construction / Ops
38
Asset goes live (Live Más)
REMODEL PIPELINE
Remodels in process
Construction
15
Keeps image current; flags slips
RENEWAL TRACKER
Lease renewals (asset mgmt)
RE / Legal
18
Option-notice = unforgiving gate
OPEN RESTAURANTS — MASTER
Operating truth + financials
Finance/Legal + All
21
THE master every tab feeds

## Slide 21
PIPELINE PLAYBOOK
QA SELF-TEST
TACO BELL | ARN
21
SIP
›
Pre-DD
›
Due Dil.
›
Committee
›
Openings
›
Master
↳ WORKBOOK INTEGRITY — runs across every tab (a hidden self-test, not a stage in the line)
ROLE IN THE LIFECYCLE
Self-testing — live tripwires run every time the file opens.
Why it's critical
Catches broken links, missing required fields and lifecycle conflicts before they reach Rob or Mazen.
OWNER
Advisor / Ellis Advisors
TASKS / FIELDS TRACKED: 10
TRACKS THESE FIELDS (10 total)
▪ Required fields present — Restaurant # · address · city · state on every record
▪ No restaurant in both OPEN and CLOSURES (lifecycle integrity)
▪ Ownership populated ≥ 197 · every leased restaurant carries rent
▪ Renewal & cell-site countdown dates resolve — no #REF!
▪ Result: 10 / 10 PASS — green means ship it

## Slide 22
PIPELINE PLAYBOOK
Approval Gates: Pre-DD → Due Diligence → RE Committee
TACO BELL | ARN
22
DD Intake = the capital request that opens due diligence. RE Committee = the Real Estate approval committee. “Pre-” = work done before that gate.
◀ THE ROADMAP — development flows left → right; each gate must clear before the next
Pre-DD
Source · tour · LOI
SIP / Pre-DD Pipeline
›
DD INTAKE
Diligence opens; capital request
Pre-DD Pipeline
›
DUE DILIGENCE
Diligence · entitlements
Due Diligence
›
RE COMMITTEE
Committee approval
Committee Approved
›
Permitting
CDs → permit
(stage)
›
Construction
Possession → build
2026 Openings
›
Open
Live Más
Master
Why the gates matter:
• A deal cannot pass a gate until its fields are complete — that's how the bible prevents missed steps.
• Capital is only at risk after DD intake; it's only committed after RE Committee approval.
• Due Diligence (diligence/entitlements) is where schedules slip — start it in parallel with legal.
• Each tab in the workbook corresponds to one of these gates; a site advances tab-to-tab.

## Slide 23
PIPELINE PLAYBOOK
SIP — Sites in Process
TACO BELL | ARN
23
SIP
▼ YOU ARE HERE
›
Pre-DD
›
Due Dil.
›
Committee
›
Openings
›
Master
ROLE IN THE LIFECYCLE
Stage 1 — site inception. Every candidate site enters here from touring; the data lifecycle starts at this tab.
Why it's critical
Discipline here protects the whole funnel — only strategy-aligned sites should advance.
OWNER
Real Estate
TASKS / FIELDS TRACKED: 41
TRACKS THESE FIELDS (41 total)
▪ Date Toured · Market / State · Trade Area · Intersection / Center
▪ Size · For Sale / For Lease · Price · Offer
▪ Aerial · Site Plan · Flyer (links)
▪ STATUS · Stage · RISK (stoplight)
▪ Lead · Next Step · Next Step Due · Action Flag
▪ Days Since Toured · Days to Open · Sched Var (auto)

## Slide 24
PIPELINE PLAYBOOK
Pre-DD Pipeline
TACO BELL | ARN
24
SIP
›
Pre-DD
▼ YOU ARE HERE
›
Due Dil.
›
Committee
›
Openings
›
Master
ROLE IN THE LIFECYCLE
Stages 2–3 — sourcing through LOI, before due diligence opens (the capital request).
Why it's critical
Captures the deal and its terms before any capital is requested; LOI dates time the front of the funnel.
OWNER
Real Estate
TASKS / FIELDS TRACKED: 33
TRACKS THESE FIELDS (33 total)
▪ Proj # · Project Name · City / ST
▪ Roles (Real Estate / Construction / Legal / Ops / Exec)
▪ Risk · Drive-Thru
▪ LOI Sent · LOI Executed
▪ RE Committee target date · Lease Status

## Slide 25
PIPELINE PLAYBOOK
Due Diligence
TACO BELL | ARN
25
SIP
›
Pre-DD
›
Due Dil.
▼ YOU ARE HERE
›
Committee
›
Openings
›
Master
ROLE IN THE LIFECYCLE
Stage 4 — diligence & entitlements, after DD intake and before RE Committee approval.
Why it's critical
Proves the site is buildable. This is the #1 place schedules slip — run it in parallel with legal.
OWNER
Real Estate / Legal
TASKS / FIELDS TRACKED: 34
TRACKS THESE FIELDS (34 total)
▪ DD intake date · Committee target date
▪ Re-Plat start / complete
▪ Site / Floor Plan · Signage research
▪ ALTA Survey · Phase I environmental
▪ A&C package · intake → approval duration

## Slide 26
PIPELINE PLAYBOOK
Committee Approved
TACO BELL | ARN
26
SIP
›
Pre-DD
›
Due Dil.
›
Committee
▼ YOU ARE HERE
›
Openings
›
Master
ROLE IN THE LIFECYCLE
Stage 5 — capital approved at the RE Committee.
Why it's critical
The go / no-go capital gate — nothing builds without it.
OWNER
Exec / Finance
TASKS / FIELDS TRACKED: 37
TRACKS THESE FIELDS (37 total)
▪ RE Committee (approval) date
▪ Risk · Lease Status
▪ Permit Ready · Possession date
▪ Start Construction · Sched Opening
▪ Period Opening

## Slide 27
PIPELINE PLAYBOOK
2026 Openings YTD
TACO BELL | ARN
27
SIP
›
Pre-DD
›
Due Dil.
›
Committee
›
Openings
▼ YOU ARE HERE
›
Master
ROLE IN THE LIFECYCLE
Stages 7–8 — construction to open (Live Más); the YTD opened/opening list.
Why it's critical
Where the asset goes live; the 90-day post-open review feeds truth back to the Master.
OWNER
Construction / Ops
TASKS / FIELDS TRACKED: 38
TRACKS THESE FIELDS (38 total)
▪ Possession · Start Const · Sched / Actual Opening
▪ Rent Commencement
▪ FF&E Order · Staffing / Training Start
▪ Certificate of Occupancy (CO)
▪ 90-Day Post-Open Review · Free Food Day (optional)

## Slide 28
PIPELINE PLAYBOOK
REMODEL PIPELINE
TACO BELL | ARN
28
SIP
›
Pre-DD
›
Due Dil.
›
Committee
›
Openings
›
Master
↳ PARALLEL TRACK — Asset Management (runs alongside the pipeline — not a stage in the line)
ROLE IN THE LIFECYCLE
Asset management — remodels in process (from the 5/27/26 list).
Why it's critical
Keeps the image current; Flags surface discrepancies and EXPIRED dates automatically.
OWNER
Construction
TASKS / FIELDS TRACKED: 15
TRACKS THESE FIELDS (15 total)
▪ Image / Prototype · Action (Mid-term / Successor)
▪ Date Due · Date Status (EXPIRED / Due Soon / On Track)
▪ FDD Received · RE Committee Order
▪ Material Delivery · Construction Schedule
▪ Flags (past due / missing FDD / not scheduled)

## Slide 29
PIPELINE PLAYBOOK
RENEWAL TRACKER
TACO BELL | ARN
29
SIP
›
Pre-DD
›
Due Dil.
›
Committee
›
Openings
›
Master
↳ PARALLEL TRACK — Asset Management (runs alongside the pipeline — not a stage in the line)
ROLE IN THE LIFECYCLE
Asset management — lease renewals (measured separately from the development pipeline).
Why it's critical
Protects the existing portfolio; the option-notice date is an unforgiving, hard gate.
OWNER
Real Estate / Legal
TASKS / FIELDS TRACKED: 18
TRACKS THESE FIELDS (18 total)
▪ Sales · SOP · Occ % (performance)
▪ Term End · LL Notice Date · Options · Auto-Renew
▪ Days to Notice · Notice Status (auto RAG)
▪ Priority Tier (1 / 2 / 3) · Renewal Status · Owner
▪ Dated & attributed notes — M/D/YY (initials)

## Slide 30
PIPELINE PLAYBOOK
CELL SITES
TACO BELL | ARN
30
SIP
›
Pre-DD
›
Due Dil.
›
Committee
›
Openings
›
Master
↳ PARALLEL TRACK — Asset Management · ARN is the LANDLORD (ancillary income — rent flows IN to ARN)
ROLE IN THE LIFECYCLE
Ancillary income — carrier ground / rooftop leases where ARN collects rent.
Why it's critical
High-margin income with long escalators; the reset date is the leverage moment — model it before the carrier does.
OWNER
Advisor / Real Estate
TASKS / FIELDS TRACKED: 2
TRACKS THESE FIELDS (2 active)
▪ AT&T D-003 (5654 Greenwood Plaza, CO) — 25% / term escalator since 2000 has pushed rent ABOVE market
▪ Play: defend the legacy rate at the ~2030 reset — don't let AT&T rebase
▪ T-Mobile DN06142A — counter modeled $4,000–$4,400 / mo vs. their $3,900 offer
▪ Tracks: Carrier · Lease ID · Current Rent · Escalator · Reset / Expiry (auto countdown)
▪ Landlord test: at / above market + total over term — not occupancy

## Slide 31
PIPELINE PLAYBOOK
EXCESS PROPERTIES
TACO BELL | ARN
31
SIP
›
Pre-DD
›
Due Dil.
›
Committee
›
Openings
›
Master
↳ PARALLEL TRACK — Asset Management · owned non-restaurant parcels (idle owned land & buildings — lease or sell)
ROLE IN THE LIFECYCLE
Owned land & buildings that are not restaurants — to be leased out or sold.
Why it's critical
Idle owned assets carry cost and tie up capital; each needs a disposition decision and a broker.
OWNER
Advisor / Real Estate (src: JD)
TASKS / FIELDS TRACKED: 9
TRACKS THESE FIELDS (9 parcels)
▪ 9 parcels — NM 5 · CO 2 · VA 1 · WI 1
▪ Types: raw dirt · empty former-TB buildings · leased tenant spaces
▪ Tracked like a cell site: ID · Address · City / State · Type · Disposition · Value · Status · Broker
▪ e.g. EX-001 Coors & Central (ABQ, dirt) · EX-006 Exmore VA (former TB)
▪ Open items: valuations · zoning · lease-vs-sell call · broker + title / easement check

## Slide 32
PIPELINE PLAYBOOK
OPEN RESTAURANTS — MASTER
TACO BELL | ARN
32
SIP
›
Pre-DD
›
Due Dil.
›
Committee
›
Openings
›
Master
▼ YOU ARE HERE
ROLE IN THE LIFECYCLE
The Single Source of Truth: all operating restaurants plus financial performance. Every other tab feeds or draws from here.
Why it's critical
THE master. Locked finance/legal columns protect the truth; operational fields stay editable.
OWNER
Finance/Legal (locked $) + All
TASKS / FIELDS TRACKED: 21
TRACKS THESE FIELDS (21 total)
▪ Restaurant # · Operator / Partner (ARN / ALBOR) · State · City · Address
▪ Open Date · Sq Ft · Drive-Thru · Own / Lease
▪ 2025 Sales · SSS YoY · SOP · Occ % (LOCKED)
▪ Lease Expiration · Franchise Exp (LOCKED)
▪ Status · Last Updated · Updated By · dated Notes

## Slide 33
TACO BELL | ARN
Strategy — The Growth Engine
Strategy defines the hunt; the hunt fills the pipeline; openings become truth; truth sharpens strategy.

## Slide 34
PIPELINE PLAYBOOK
The Strategy Loop
TACO BELL | ARN
34
A closed loop — data starts at inception (SIP) and matures into the Master, which recalibrates the next strategy.
STRATEGY
Where to grow & defend
›
HUNT — SIP
Source sites that fit
›
BUILD
Advance the pipeline
›
OPEN · Live Más
New restaurant goes live
›
TRUTH — Master
Actuals update the SSOT
↺ Feedback: the Master's truth (sales, SOP, impact) flows back to recalibrate Strategy — the loop repeats and sharpens each cycle.
In the workbook: Strategy = YUM Deep Dive + Master tiers → Hunt = SIP → Build = Pre-DD / Due Diligence / Committee Approved → Open = 2026 Openings → Truth = Open Restaurants Master (which feeds the dashboards & the next hunt).

## Slide 35
PIPELINE PLAYBOOK
Inputs to Strategy — Where to Grow & Defend
TACO BELL | ARN
35
STRATEGY
▼ YOU ARE HERE
›
HUNT · SIP
›
BUILD
›
OPEN
↻
TRUTH
YUM Whitespace
“Holes in the market for new-restaurant growth” — parent-co Bell Point / Intalytics forecasts & impact. Target Growth-priority trade areas.
Portfolio Performance
The Master's sales / SSS / SOP tiers — double down where strong, fix or exit where red.
Base Protection
Renewals (option-notice critical dates) & remodels keep the existing portfolio healthy and current.
Competition
QSR competitive comps & sales in the 2-mi trade area — and cannibalization of our own restaurants.
Strategy = grow into YUM whitespace where ARN can beat the forecast, defend the strong base, and avoid cannibalizing ourselves.

## Slide 36
PIPELINE PLAYBOOK
The Hunt — SIP Criteria from Strategy
TACO BELL | ARN
36
STRATEGY
›
HUNT · SIP
▼ YOU ARE HERE
›
BUILD
›
OPEN
↻
TRUTH
Strategy turns into a filter for the SIP hunt. A site advances only if it clears these:
Trade-area fit
Falls in a YUM Growth whitespace (or a proven ARN gap) — link the DMATA on SIP.
Beats the forecast
ARN projection ≥ YUM Bell Point midpoint (ARN vs YUM tab, Δ% green).
Drive-thru & access
Site supports the prototype, stacking, and signalized access.
Co-tenancy & traffic
Anchors / QSR draw and traffic counts support the daypart mix.
Low cannibalization
No heavy impact on our own restaurants — avoid a new site within ~2 mi of a <$2M ARN restaurant.
Fair-market deal
Rent / price pencils to the proforma; clean control of the asset.

## Slide 37
PIPELINE PLAYBOOK
The Feedback Loop — Open Becomes Truth
TACO BELL | ARN
37
STRATEGY
›
HUNT · SIP
›
BUILD
›
OPEN
↻
TRUTH
▼ YOU ARE HERE
Once open, the restaurant's reality flows back into the system and sharpens the next hunt:
▪ Restaurant opens (Live Más) and the lease abstract + dates load into the Master & Renewal Tracker.
▪ 90-day post-open review captures actual sales, SOP and daypart mix.
▪ The Master re-tiers the restaurant (green / amber / red) — and shows actual vs the YUM forecast that justified it.
▪ Wins & misses recalibrate Strategy: where the forecast held, hunt similar whitespace; where it missed, adjust the filter.
▪ Renewals & remodels keep that restaurant healthy so it stays a green contributor.
The payoff: every cycle the forecasts get truer, the hunt gets sharper, and capital goes to the holes most likely to become green restaurants.

## Slide 38
TACO BELL | ARN
Run the playbook.
Disciplined sequence. Owned steps. Stoplight visibility. A schedule that holds — so guests Live Más.
Built fresh. Made to order. Served on time.
“We focus on making the tacos, not the sausage.”
TACO BELL | ARN — Field Development

## Slide 39
TACO BELL | ARN
The Next Evolution — the KEA Platform
The Bible's logic lifted into a branded web app — drill into any restaurant, build any report, no spreadsheet required.
Same single source of truth — a friendlier front door.
“It does what Lucernex and Accruent do — at a fraction of the cost.”
KIM ELLIS ADVISORS · Portfolio Lifecycle Platform

## Slide 40
TACO BELL | ARN
Exhibits & Templates
Exhibit A — Site Package (NRO Committee) · Exhibit B — Renewal Evaluation Sheet

## Slide 41
PIPELINE PLAYBOOK
Exhibit A — Site Package (NRO Committee)
TACO BELL | ARN
41
The standard 17-section Real Estate Committee package for a new restaurant opening — example: Lobo Village (I-25 & Gibson, ABQ).
Cover
Deal Summary
Deal Terms
Includes:
▪ Deal Summary & Site Highlights
▪ Deal Terms (site / rent / construction / proforma)
▪ Site Scorecard
▪ Market Strategy Map
▪ Aerials / Site Plan / Interior
▪ Signage & Photos
▪ Contract Standard Deviations
▪ Market Comps (lease / purchase)
▪ QSR Competition (2-mile radius)
▪ Milestone Timeline & Approvals
All package pages follow — populated with the live Lobo Village deal data & links. Editable file: “ARN Taco Bell – Lobo Village Site Package.pptx”

## Slide 64
PIPELINE PLAYBOOK
Exhibit B — Renewal Evaluation Sheet
TACO BELL | ARN
64
Per-restaurant lease evaluation (Operating Restaurant — Key Lease Detail), TB/ARN branded. Companion to the Renewal Tracker.
Restaurant Info
Restaurant #
Restaurant Name
Open Date
Sq Ft
Location Type
Address
City / State
Performance
2025 Sales
YoY 24→25
SOP Margin
Occupancy %
Lease Terms & Rent
Deal Type
Expiration Date
Rent Commencement
Max LXD
Options Remaining
Option Notice Date
Existing Rent
Option Rent / Escalations
Lease Provisions
Co-Tenancy
Exclusive Use
CAM / Admin
% Rent
Go Dark / Radius
Renewal Strategy
Decision (Renew / Renegotiate / Relocate / Close)
Strategy & Levers
Anticipated LL Position
Misc & Landlord
Committee Approved
Lease Critical Date
Landlord
LL Contact / Phone
Approvals
Real Estate
Legal
Exec